As of 9/23/17

RETREAT PLANNING TIMELINE

DATE:  TBD

PLACE:  TBD

THEME:  TBD

GUEST SPEAKER/PRESENTOR:  TBD

HOST CONTACTS:   TBD

The planning committee is a team of people who will help in the following categories:

Publicity, Hospitality, Food, Registration, Agenda, Guest Speaker, Prayer Team, Budget, Breakout Sessions, Craft Session, Gift Bags, Hotel Recommendations, Worship Service, etc.  The Planning committee usually does not meet in November and December.

PRAYER TEAM - As soon as possible & through the day of the event

• Meet at specified times for group prayer

• Go to location before the event for prayer

• Make a commitment to pray on your own as well

1 YEAR OUT - April:

- Date and location needs to be determined for the coming year

- Date is usually in early April and announced at the current year’s Retreat

- Host church needs to get date on their church calendar

7 MONTHS OUT - September

- Design Save the Date announcement

- Secure guest speaker

- Get on the NTNL and WELCA calendars

6 MONTHS OUT - October

- Send Save the Date announcement to all churches in region

- Secure worship leader for communion worship service

- Secure outside presentation leaders, if any,  ie:  Wells for Water, etc

3 MONTHS OUT - January

- Design posters, flyers, and/or brochures. Also, a bulletin size poster.

- Design registration forms

- Gather contact names and numbers for all the churches in region

- Create list of hotels near host church; post on website; send to planning committee

- Determine budget to include guest speaker and registration costs

- Apply for Thrivant funds

RETREAT PLANNING OUTLINE………….page 2

2 MONTHS OUT - February

- Send registration forms to all churches in region

- Post registration form on website

- Target other churches and distribute posters/flyers

- Post flyer/brochure on Website

- Make announcements and promotion in host church

- Determine food options/menu

- Book caterer if meal is to be catered

- Secure pianist for worship service

1 MONTH OUT - March

- Follow up calls or onsite meetings with target churches

- Designate who will be helping and determine their assignments

- Determine how/where the check-in and greeting process will flow, where breakout session will be held, where guest speaker will be, etc.  Assign rooms for each agenda item

- Food – if homemade - determine menu and who will prepare the food

- Create nearby restaurant list/directions (to be distributed at registration)

- Plan afternoon/evening snacks

- Collect registration forms and fees

- Send registration headcount to planning committee members

- Assign break-out session leaders

3 WEEKS OUT – Mid March

- Place newspaper ad to promote retreat or concert

2 WEEKS OUT – Late March

- Follow up with announcements and promotion in host church

- Send registration headcount to planning committee members

1 WEEK OUT

- Send registration headcount to planning committee members

- Make gift bags for every woman attending, plus 8 - 10 extra ones

RETREAT PLANNING OUTLINE………….page 3

DAY BEFORE EVENT

- Set up breakout session rooms

- Set up crafts

- Decorate tables for luncheon

- Set up snack area for breaks

- Set up registration table and gift bag table

- Post signage

- Print off agendas

- Prep name tags and alphabetize tags

- Set up and test A/V equipment

- Prep food

DAY OF EVENT

- Register women    (Be there 1 hour prior for early arrivals)

- Registration should include name tag, agenda, restaurant info, gift bag, survey

- Direct women during breaks and breakout sessions

2 – 3 WEEKS AFTER EVENT

- Have a recap meeting to discuss the survey results and how to improve retreats going forward

BREAKOUT SESSIONS

- Breakout sessions are smaller groups where the goal is to share information, or a Bible study, or an opportunity where “getting real” would really start to happen.

- Depending on the number of breakout sessions, they can run 20 min to 1 hour each.

- The breakout session leader talks about her subject, then leaves time for discussion questions, and facilitates a group discussion.

- The leader must be able and willing to steer the group and the discussion in a godly manner and keep it on point.

- One of the breakout sessions can be a craft time

- The last 5 to 10 minutes could be used for group prayer time

- Name tags should have a designation, such as a colored dot, to divide up the group so that everyone has an opportunity to attend all of the breakout sessions scheduled

(ie:  Yellow for Group 1, Blue for Group 2, Red for Group 3)

Below are two suggested agenda formats….one with a concert/musical venue and one without.

SUGGESTED AGENDA (for a 1 day event, no concert)

SATURDAY

| 9:00-9:30am | Registration | 30 min |
| --- | --- | --- |
| 9:30-11:00am | Keynote Speaker/Presentation | 90 min |
| 11:00-11:15am | Break | 15 min |
| 11:15-12:00noon | Program/Presentation | 30 min |
| 12:00 – 1:00pm | Lunch | 60 min |
| 1:00 – 1:25pm | Breakout/Craft Session #1 | 25 min |
| 1:25 – 1:35pm | Break | 10 min |
| 1:35 – 2:00pm | Breakout/Craft Session #2 | 25 min |
| 2:00 – 2:10pm | Break | 10 min |
| 2:10 – 2:35pm | Breakout/Craft Session #3 | 25 min |
| 2:35 – 2:45pm | Break | 10 min |
| 2:45 – 3:15pm | Worship Service w/Communion | 30 min |
| 3:15 – 3:45pm | Closing Remarks | 30 min |

SUGGESTED AGENDA (for a 2 day Event/Concert)

FRIDAY NIGHT

| 4:00–7:00 | Registration/Gathering Time | 3 hrs |
| --- | --- | --- |
| 7:00–8:15 | Welcome/Concert | 75 min |
| 8:15–8:30 | Ice Breakers | 15 min |
| 8:30–? | Get Crazy Time! |  |

SATURDAY

| 8:00–9:00am | Breakfast/Registration | 60 min |
| --- | --- | --- |
| 9:00–10:30am | Keynote Speaker | 90 min |
| 10:30 – 10:45am | Break | 15 min |
| 10:45–11:45 | Breakout Session | 60 min |
| 11:45 - 12:45pm | Lunch/Musical Program/Entertainment | 60 min |
| 1:15–2:30 | Program/Presentation | 75 min |
| 2:30 -2:45pm | Break | 15 min |
| 2:45–3:30 | Breakout Sessions/Craft Session | 45 min |
| 3:30 – 3:45pm | Break | 10 min |
| 3:45 - 4:15pm | Worship Service w/Communion | 30 min |
| 4:15 – 4:45pm | Closing Remarks | 30 min |